## Abhishek
Week
Team Members | 24-Feb | 3-Mar | 10-Mar | 17-Mar | 24-Mar | 31-Mar | 7-Apr | 14-Apr | 21-Apr | 28-Apr
Tianqi | Architectural Review | Processor Architecture | Processor Design | Processor: Fetch, Execute, and Hazard Detection | Spring Break | Processor: Verify and Debug
Han | Architectural Review | Accelerator Architecture | Accelerator Design | Finish Systloic Array and AI Model Array | Spring Break | Accelerator: Continue Work On
Allie | Architectural Review | Memory Architecutre | Processor Design | Processor: Decode, Memory, WriteBack, and Top Level | Spring Break | Memory: SDRAM and AXI Interface
Jingyu | Architectural Review | Processor Verification/Compiler | Processor Verification | Finish Assembly Tests for Processor Verification | Spring Break | Processor: Verify and Debug